## Slide 1
Uzbekistan Eco-Industrial Parks (EIP) Project
work plan 2026–2027
by T.Chernyavskaya, Project Manager
Steering Committee Meeting
26.06.2026
Notes: Opening: this presentation focuses on the proposed next phase of the Uzbekistan EIP Project. The message is that Phase I has generated evidence, capacities and a project pipeline; Phase II will move from demonstration to replication and institutionalization.

## Slide 2
2
Phase II: from demonstration to scale-up
Strategic purpose of the 2026–2027 phase
Overall objective
Scale up and replicate the implementation of Eco-Industrial Park approaches by industrial zones and tenant companies in Uzbekistan.
Deepening and Continuity
Continue implementation support in the two Phase I pilot zones: FEZ “Urgut” and SIZ “Fergana Mechanic”.
Replication
Target additional industrial parks to increase visibility of economic, environmental and social benefits.
Greenfield support
Assist the preparation of an EIP concept and master plan for a selected greenfield or newly developed industrial park.
Policy and capacity
Operationalize EIP policy instruments, deepen national capacities and connect the project pipeline to future investments.
Notes: Key speaking point: Phase II is not a separate concept. It builds directly on Phase I and has two directions: deepening the existing pilot sites and expanding EIP implementation to additional zones, including FEZ Navoi and a greenfield or newly developed park.

## Slide 3
3
Phase I (2024-2025) foundation: why scale-up is feasible
The next phase builds on evidence, tools, trained experts and investment-ready ideas
20
companies assessed under RECP in pilot zones
90+
RECP measures identified
22
national experts trained in RECP / EIP-related areas
2
policy documents drafted for EIP institutionalization
2
pilot zones with EIP roadmaps and monitoring tools
Feasibility work advanced on solar PV, heat pumps, wastewater treatment and selected industrial synergies.
Pilot zones and resident companies have generated a practical pipeline for investment and replication.
Project visibility and stakeholder ownership increased through SC meetings, workshops, national conference and media outreach.
Notes: Use this slide to remind SC members that the project has already moved beyond awareness. It has produced technical evidence, draft legal instruments, trained human capacity, and a project pipeline. The numbers are only highlights; detailed evidence is available in the Yearly Report.

## Slide 4
4
Phase II (2026–2027) results framework
Two outcomes structure the next phase
Outcome 3
Deepening and scaling up EIP implementation
Improved environmental performance in Urgut FEZ and Fergana Mechanic SIZ
Expansion to additional park(s) and zone(s)
Feasibility studies, roadmaps and implementation support
Outcome 4
Policy, knowledge transfer and capacity building
Capacity-building for park management, companies and service providers
Operationalization of EIP policy instruments and incentives
Monitoring, verification and reporting on EIP performance
Cross-cutting: gender equality • environmental & social safeguards • results-based monitoring • communications
Notes: The main message is that activities are organized around two results areas: practical implementation and national institutionalization. The cross-cutting elements should be included in all workstreams, not treated as separate add-ons.

## Slide 5
5
Workstream A — deepen results in FEZ “Urgut” and SIZ “Fergana Mechanic”
Move from assessment and feasibility to implementation support and monitoring
1. Technical assistance
Support implementation of prioritized EIP and industrial-symbiosis measures, including energy, water, raw material use, waste and emissions control.
2. Additional assessments
Conduct RECP assessments in 20 more tenant companies and explore RECP clubs to sustain company-level implementation.
3. Investment decisions
Prepare detailed feasibility studies, engineering support and bankable project documentation for selected EIP/RECP measures.
4. Continuous monitoring (phase I & phase II)
Systematically track RECP, EIP and environmental performance indicators and prepare case studies on technical and economic results.
Priority themes
Renewable energy • wastewater and water reuse • waste and hazardous waste management • energy management systems and standards.
Notes: Explain that the existing pilots remain essential. Phase II should help convert technical recommendations into measurable outcomes, while keeping Urgut and Fergana Mechanic as reference sites for national replication.

## Slide 6
6
Workstream B — FEZ “Navoi” as a scale-up site
Build on the Phase I selection experience and recent mission dialogue
1
Confirm cooperation
Directorate, regional authority and focal points
2
Baseline EIP assessment
Management, environmental, social and economic performance
3
Company screening
Select resident companies for RECP: energy / water / waste diagnostics
4
EIP roadmap
Quick wins and medium-term investment priorities and synthesys opportunities
5
Feasibility & finance
Prepare bankable project fiches and partner outreach
Proposed assessment themes: energy efficiency, PV readiness, water and wastewater, waste valorization, industrial symbiosis, park services and social performance.
Selection of companies is data-driven and agreed with FEZ management to ensure ownership and access to operational data.
Notes: Present FEZ Navoi as a practical replication case. Avoid overpromising before assessments are complete. Emphasize an orderly sequence: confirm partnership, assess baseline, select companies, prepare roadmap, then package projects for finance and technical assistance.

## Slide 7
7
Workstream C — identify and support a greenfield / newly developed park
Use EIP-by-design principles before infrastructure and tenant patterns are locked in
Selection approach
Apply UNIDO’s EIP Selection Tool to identify, review and prioritize candidate sites in a transparent and methodological way.
Key criteria
Government commitment • master plan status • infrastructure readiness • tenant pipeline • resource efficiency potential • environmental and social risks.
EIP-by-design focus
Integrate resource-efficient infrastructure, shared utilities, renewable energy, water reuse, waste services, safe mobility and inclusive social infrastructure.
Expected outputs
EIP concept plan + reviewed master plan + prioritized opportunity list + investment and partnership needs
Notes: This slide is important for international partners because a greenfield site creates the opportunity to integrate EIP principles from the planning stage. This can reduce future retrofit costs and create a stronger demonstration case.

## Slide 8
8
Workstream D — legal and policy work, including Energy Efficiency Agency engagement
Translate Phase I policy outputs into operational mechanisms
Support implementation of the Presidential Decree on EIPs and operationalization of Cabinet of Ministers documents introducing Eco-Industrial Zones.
Clarify EIP criteria, institutional roles, incentives, reporting requirements and monitoring / verification mechanisms.
Facilitate continued policy dialogue with ministries, agencies, park directorates, companies and development partners.
Energy Efficiency Agency engagement
Integrate EIP principles into national energy-efficiency advisory and support mechanisms.
Support energy management, MRV of savings, standards and project pipeline linkages.
Coordinate with PV, heat-pump, BESS and industrial energy-efficiency opportunities.
Policy outcome sought: a practical framework that enables parks and companies to identify, finance, implement and report EIP measures.
Notes: Link this slide to the needs of government stakeholders and donor partners. Phase I produced a policy package; Phase II should focus on implementation, roles, incentives, reporting and practical integration with national energy efficiency work.

## Slide 9
9
Proposed company assessment package
A consistent service package for existing pilots, FEZ “Navoi” and selected new parks
Target groups
ALready engaged and additional tenant companies in FEZ Urgut and SIZ Fergana Mechanic; selected FEZ Navoi resident companies; anchor and future tenants in selected greenfield/new parks.
Assessment methods
Rapid RECP diagnostics; detailed RECP and feasibility assessment; EIP opportunity screening; investment pre-screening; environmental and social performance checks.
Priority themes
Energy efficiency; wastewater treatment and reuse; waste valorization; energy management systems; industrial symbiosis.
Outputs for companies and partners
Implementation action plans with roles and timelines
Project fiches for financing and technical assistance
Case studies documenting cost savings, resource savings and CO₂ reductions
Data for national EIP monitoring and future policy reporting
Notes: This slide should help SC members understand what “company assessments” will produce in practical terms. It also clarifies the value for potential development partners: assessments lead to a portfolio of projects that can be supported by grants, concessional finance or technical assistance.

## Slide 10
10
Indicative implementation squedule
A practical 2026–2027 roadmap for coordination and partner engagement
2026 Q1
Policy work, SC endorsement
Site & focal point confirmation
Navoi/greenfield scoping
2026 Q2
Baseline assessments
Company selection
Policy consultations
2026 Q3
Roadmaps
Feasibility studies
EE Agency workstream
2026 Q4
Investment decisions
Case studies
Monitoring update
2027 H1
Implementation support
Replication package
Capacity building
2027 H2
Policy roll-out
Final lessons
Scale-up pipeline
SC coordination checkpoints: Q2 2026 launch • Q4 2026 progress review • Q2 2027 replication and sustainability review
Source: Amended ProDoc, Phase II timeline of activities.
Notes: Use this as a coordination slide. The exact dates may be adjusted after SC guidance, but the sequence should remain: confirm sites and data access, assess, design roadmaps and feasibility, support investments, monitor and disseminate.

## Slide 11
11
Support requested from the Steering Committee and partners
Decisions and coordination needed to start Phase II efficiently
1. Confirm priority sites
Confirm FEZ “Navoi” as a scale-up site and agree on the process for identifying the greenfield/newly developed park.
2. Nominate focal points
Designate working-level focal points from ministries, agencies, park directorates and relevant technical institutions.
3. Facilitate data access
Support timely collection of park-level and company-level data required for EIP, RECP and feasibility assessments.
4. Align policy work
Support operationalization of EIP legal instruments. Coordination with the Energy Efficiency Agency.
5. Mobilize investments
Coordinate partner support around a pipeline of bankable RECP, energy, water, waste and symbiosis projects.
6. Communicate results
Use success stories and monitoring data to build demand for EIP services across Uzbekistan.
Notes: Close the substantive part with clear asks. The Steering Committee is invited to support site confirmation, focal point nomination, data access, policy alignment and investment mobilization. This makes the presentation decision-oriented.

## Slide 12
12
Thank you for your attention!
www.ecoindustrialparks.uz
This activity is implemented by United Nations Industrial Development Organization in the framework of Grant Agreement funded by the German Federal Ministry for Economic Cooperation and Development (BMZ) and supported by Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.
Notes: Final slide. Invite questions and partner comments on the proposed 2026–2027 priorities.